## Test Case Tracker
Test Case ID | Module | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Priority | Type | Tested By | Date Tested | Environment | Notes
TC_BB_001 | Functional | Selecting a service updates UI state | 1. Open site 2. Click a service option | Any service | Selected service is visually highlighted/marked as active | Service selection visibly highlights on click; deselects previous on new click | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px & Chrome 128, Windows 11, Desktop DevTools @ 390px & Chrome Mobile, Android 14, TECNO Pro, 390px
TC_BB_002 | Functional | Selecting a city updates UI state | 1. Open site 2. Click a city option | Any city | Selected city is visually highlighted/marked as active | City selection visibly highlights on click; tested all cities in list, no overflow/registration issues | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px & Chrome 128, Windows 11, Desktop DevTools @ 390px & Chrome Mobile, Android 14, TECNO Pro, 390px
TC_BB_003 | Functional | Service+city generates correct WhatsApp message | 1. Select a service 2. Select a city 3. Click Book Now | Service=X, City=Y | WhatsApp opens with message containing exact service X and city Y | WhatsApp message correctly shows selected service and city, no undefined/broken strings | Pass | High | P1 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px & Chrome 128, Windows 11, Desktop DevTools @ 390px & Chrome Mobile, Android 14, TECNO Pro, 390px
TC_BB_004 | Functional | Message content matches exact selection (no mismatch) | 1. Select Service A + City B 2. Inspect generated message text | Service A, City B | Message text says Service A and City B, not any other combination | Changing service while city stays fixed correctly updates message with no leftover values | Pass | High | P1 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px & Chrome 128, Windows 11, Desktop DevTools @ 390px & Chrome Mobile, Android 14, TECNO Pro, 390px
TC_BB_005 | Functional | WhatsApp link uses correct phone number and URL scheme | 1. Trigger booking 2. Inspect the href/link before it opens | N/A | Link matches wa.me/<correct number> or api.whatsapp.com/send with correct number | Inspected CTA href via DevTools. Link format: https://api.whatsapp.com/send/?phone=919615920005&text=Hello..+I+want+your+cleaning+services&type=phone_number&app_absent=0. Correct scheme, phone number matches business number digit-for-digit, text properly URL-encoded (spaces as +), redirects successfully to WhatsApp app with pre-filled chat. | Pass | Critical | P1 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px & Chrome 128, Windows 11, Desktop DevTools @ 390px & Chrome Mobile, Android 14, TECNO Pro, 390px
TC_BB_006 | Functional | Booking completes quickly with no extra steps | 1. Time yourself from landing to WhatsApp opening | N/A | Flow completes in well under 10 seconds with no unnecessary clicks | Timed 3 trials from page-interactive to WhatsApp opening: Trial 1 = 3s, Trial 2 = 4s, Trial 3 = 6s. Average = 4.3s. | Pass | Low | P3 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px & Chrome 128, Windows 11, Desktop DevTools @ 390px & Chrome Mobile, Android 14, TECNO Pro, 390px
TC_BB_007 | Functional | Behavior when only service selected (no city) | 1. Select a service only 2. Attempt to click Book Now | Service=X, City=None | Button disabled OR clear prompt to select a city (no silent failure) | Site loads with a default city pre-selected. There is no reachable UI state where city is empty while a service is selected — user cannot deselect the default city through normal interaction. | N/A | Medium | P2 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px | Original test assumed city could be left unselected. App pre-fills a default city on load, making this state unreachable via UI. See TC_BB_007b for follow-up test.
TC_BB_008 | Functional | Behavior when only city selected (no service) | 1. Select a city only 2. Attempt to click Book Now | Service=None, City=Y | Button disabled OR clear prompt to select a service | Selected a city only, did not select any service, clicked Book Now. App did not block the action or show validation — redirected to WhatsApp with message "Hello.. I want your cleaning services," defaulting to "cleaning" despite no service being selected. | Fail | Medium | P2 | Manual & Automated | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px | Asymmetric bug vs TC_BB_007: city has a visible intentional default, but service silently falls back to "cleaning" with no visible selection or user awareness. Confirmed via automated Cypress test (booking-flow.cy.js) — see BUG_BB_001.
TC_BB_009 | Functional | Behavior when nothing selected and user proceeds | 1. Load site fresh 2. Immediately click Book Now | No selections | Button disabled OR validation message shown, no crash/blank message | Loaded page fresh, clicked Book Now immediately without any interaction. No block or validation shown — redirected to WhatsApp with message "Hello.. I want your services," using generic placeholder text instead of a specific service name. | Fail | Medium | P2 | Manual & Automated | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px | Same root cause as TC_BB_008 (no service validation) but message text differs — "your services" here vs "cleaning services" in TC_BB_008, despite both having no service selected. Suggests inconsistent fallback logic. Confirmed via automated Cypress test (booking-flow.cy.js) — see BUG_BB_001.
TC_BB_010 | Functional | Re-selecting different service/city updates message | 1. Select Service A + City B 2. Change to Service C + City D 3. Click Book Now | A/B then C/D | Final message reflects C+D only, no leftover A/B text | Selected Service A + City B, then changed selection to Service C + City D, clicked Book Now. Message correctly reflected only C+D with no leftover A/B values — state re-computed correctly on re-selection. | Pass | High | P1 | Manual | Kolli Balaji | 2026-08-29 | Chrome 151, Windows 11, Desktop, 1440px
TC_BB_011 | Functional / Routing | Back-navigation via mobile swipe gesture after multi-selection results in blank/404 page | 1. Select multiple services on mobile\n2. Perform right-to-left edge swipe gesture (native back navigation)\n3. Observe resulting page | Multiple service selections, mobile touch gesture | App returns to previous valid state or homepage, not a broken/blank page | After selecting services and swiping back (right-to-left edge gesture), site went blank and displayed a 404 Not Found page | Fail | High | P1 | Manual | Kolli Balaji | 2026-08-30 | Chrome Mobile — Android | Not caught by Cypress automation — gesture-based navigation is OS-level, outside headless browser simulation scope. Related to TC_BB_011 (back nav) and TC_BB_016 (404 handling) but new distinct failure mode. See BUG_BB_007.
TC_BB_012 | Functional | Refreshing mid-flow — selection loss behavior | 1. Make selections 2. Refresh page (F5) | Any selections | Document actual behavior — note if this matches intended UX | Made selections, hit F5. Selections reset to default state on refresh — no persistence across reload, as expected for a stateless SPA with no localStorage/sessionStorage implementation. | Pass | Low | P3 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop, 1440px
TC_BB_013 | Routing | All service x city combinations produce valid messages (spot check 5-6) | 1. Pick 5-6 varied service/city pairs from config 2. Verify each generates correct message | Multiple pairs | Every tested combination produces correctly formatted, accurate message | Tested 5-6 combinations from config including first entry, last entry, and entries with longer names — all generated grammatically correct, complete WhatsApp messages with no missing/broken values | Pass | High | P1 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop, 1440px
TC_BB_014 | Routing | Invalid/unsupported city or service via URL handled gracefully | 1. Manually edit URL to an invalid service/city param (if routed) | e.g. /book/xyz/nowhere | Graceful error/fallback page, not a blank screen or crash | App does not use URL params for service/city selection — selection is purely client-state (dropdown for city, checkbox for service), not reflected in the URL. Attempting a manipulated URL (e.g. with service/city query params) results in the same Vercel default 404 error page seen previously, not a graceful fallback. | Fail | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop | Confirms app has no route handling for service/city at all — same root cause as BUG_BB_008 (missing catch-all route). Not a "friendly error/default state" as required by pass criteria — real Vercel platform error is user-facing.
TC_BB_015 | Routing | Direct URL access to a specific service/city page loads correctly | 1. Copy a deep link URL 2. Open in new tab/incognito | Valid deep link | Page loads directly with correct service/city pre-context (if applicable) | App has no per-service or per-city routes by design — all selection happens via in-page dropdown/checkbox UI on a single URL. There is no route structure like /services/cleaning to test direct access against. | N/A | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop | Not a bug — architectural choice (single-page, client-state selection, no deep-linkable routes). Worth noting as a product/UX consideration: users currently cannot share a direct link to a pre-selected service/city combination, which may be worth a future feature discussion, but is out of scope for this test.
TC_BB_016 | Routing | 404 handling for nonexistent route | 1. Navigate to a random nonexistent path | e.g. /this-does-not-exist | Custom 404 page or graceful redirect, not a blank/broken page | Navigated to busybucketkb.vercel.app/ndf — displayed Vercel's default platform 404 page (NOT_FOUND), not a custom app-branded page. No navigation back to the app, no styling matching the site, exposes internal deployment ID. | Fail | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop, 1440px | App has no client-side 404/catch-all route configured in React Router — Vercel's hosting layer serves its default error page before the React app ever loads. Same root issue likely affects TC_BB_011b's swipe-gesture 404. See BUG_BB_008.
TC_BB_017 | UI/UX | Layout integrity at 390px | 1. DevTools > Toggle device toolbar 2. Set width to 390px 3. Scroll full page | 390px | No overlapping elements, all content visible and usable | Checked full page at 390px — no overlapping elements, all content visible and scrollable without horizontal scrollbar | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, DevTools @ 390px
TC_BB_018 | UI/UX | Layout integrity at 768px | 1. Set DevTools width to 768px 2. Scroll full page | 768px | No overlapping elements, all content visible and usable | Checked full page at 768px — layout holds, no overlap or cutoff elements | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, DevTools @ 768px
TC_BB_019 | UI/UX | Layout integrity at 1024px | 1. Set DevTools width to 1024px 2. Scroll full page | 1024px | No overlapping elements, all content visible and usable | Checked full page at 1024px — layout holds, no overlap or cutoff elements | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, DevTools @ 1024px
TC_BB_020 | UI/UX | Layout integrity at 1440px | 1. Set DevTools width to 1440px 2. Scroll full page | 1440px | No overlapping elements, all content visible and usable | Checked full page at 1440px — layout holds, no overlap or cutoff elements | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop, 1440px
TC_BB_021 | UI/UX | Typography scale holds at extreme widths | 1. Check heading/body text at 390px and 1440px | 390px, 1440px | Text remains readable, no overflow/clipping/overlap | Headings/body text checked at 390px and 1440px — no wrapping/overflow issues, golden-ratio scale holds at both extremes | Pass | Low | P3 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, DevTools @ 390px & 1440px
TC_BB_022 | UI/UX | Color contrast readability across sections | 1. Visually inspect each section's text/background contrast 2. Optionally run Lighthouse a11y audit | N/A | Text is readable against background per WCAG AA (4.5:1 for body text) | WCAG automated audit (cypress-axe) flagged contrast and layout validation errors on the page | Fail | Medium | P2 | Automated | Kolli Balaji | 2026-08-30 | Cypress (accessibility.cy.js), Chrome/Electron, https://busybucketkb.vercel.app/ | See BUG_BB_003
TC_BB_023 | UI/UX | CTAs clearly visible, not overlapped by animations | 1. Observe all animated sections 2. Check CTA visibility during animation playback | N/A | CTA remains visible and clickable at all animation states | Observed all animated sections during playback — CTAs remained visible and clickable throughout animation states | Pass | High | P1 | Manual | Kolli Balaji | 2026-08-30 | 2026-08-31
TC_BB_024 | UI/UX | Mascot animations don't obstruct clickable elements | 1. Trigger mascot hover/scroll animations near buttons 2. Attempt to click through | N/A | Buttons remain clickable, mascot doesn't block pointer events | Triggered mascot hover/scroll animations near buttons and clicked through — buttons remained functional, no pointer-blocking | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop
TC_BB_025 | UI/UX | Hover states work on desktop, don't stick on touch devices | 1. Test hover on desktop mouse 2. Test tap on mobile/touch device | Desktop + mobile | Hover effect shows on desktop; no stuck/sticky hover state on mobile after tap | Hover tested on desktop mouse — effect shows/reverses cleanly; tap-tested on mobile — no stuck hover state after tap | Pass | Low | P3 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151 Desktop + Chrome Mobile Android
TC_BB_026 | UI/UX | Scroll-triggered animations fire at correct scroll position | 1. Scroll slowly through page 2. Note where each animation triggers | N/A | Animations trigger when element enters viewport, not too early/late | Scrolled slowly through page — animations triggered at appropriate points as elements entered viewport | Pass | Low | P3 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop
TC_BB_027 | UI/UX | Success animation triggers only after real success | 1. Complete a successful booking 2. Also attempt an incomplete/failed action | N/A | Success animation shows only on actual success, never prematurely | Completed a successful booking — success animation played only on genuine success; did not trigger on incomplete/blocked attempts | Pass | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Chrome 151, Windows 11, Desktop
TC_BB_028 | Cross-Browser/Device | Consistency across Chrome, Firefox, Safari, Edge | 1. Open site in each browser 2. Compare layout and functionality | 4 browsers | Consistent layout and working functionality across all four |  | Not Run | High | P1 | Manual | Kolli Balaji
TC_BB_029 | Cross-Browser/Device | iOS Safari WhatsApp deep link behavior | 1. Open site on iPhone Safari 2. Trigger booking flow | iOS device | WhatsApp app opens correctly with pre-filled message |  | Not Run | High | P1 | Manual | Kolli Balaji
TC_BB_030 | Cross-Browser/Device | Android Chrome WhatsApp app-opening vs desktop fallback | 1. Open site on Android Chrome 2. Trigger booking 3. Repeat on desktop browser | Android + Desktop | Mobile opens WhatsApp app; desktop falls back to WhatsApp Web correctly |  | Not Run | High | P1 | Manual | Kolli Balaji
TC_BB_031 | Cross-Browser/Device | Animation performance on low-end Android device | 1. Open site on a low/mid-range Android phone 2. Observe scroll and hover animation smoothness | Low-end Android | Animations remain reasonably smooth, no major jank/freeze |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_032 | Performance | Page load time / LCP verification | 1. Open DevTools > Lighthouse tab (Incognito) 2. Run Performance audit 3. Note LCP value | Live site URL | LCP under ~2.5s (Google 'good' threshold); record actual value |  | Not Run | Medium | P2 | Manual | Kolli Balaji
TC_BB_033 | Performance | Bundle size check (JS payload) | 1. DevTools > Network tab > filter JS 2. Refresh page 3. Note total transferred size | Live site URL | Total JS payload recorded; supports 'near-zero bundle impact' claim vs 600KB-1MB 3D libraries |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_034 | Performance | Animation frame rate / jank check | 1. DevTools > Performance tab > Record 2. Scroll through animated sections 3. Stop recording, inspect FPS graph | N/A | FPS stays close to 60fps, no long red 'long task' blocks during scroll |  | Not Run | Medium | P2 | Manual | Kolli Balaji
TC_BB_035 | Performance | Time to Interactive (TTI) | 1. Run same Lighthouse audit as LCP test 2. Note TTI metric | Live site URL | TTI value recorded; reasonably fast (few seconds range) |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_036 | Accessibility | Keyboard-only navigation through booking flow | 1. Click neutral area on page 2. Use only Tab/Shift+Tab/Enter/Space 3. Attempt full booking flow | Keyboard only, no mouse | Every interactive element reachable and operable via keyboard in logical order |  | Not Run | High | P1 | Manual | Kolli Balaji
TC_BB_037 | Accessibility | Screen reader labels (aria-labels) on interactive elements | 1. Inspect each icon-only button/element 2. Check for aria-label or readable text | N/A | Every interactive element has visible text or aria-label for screen readers | Automated cypress-axe/manual inspection found mobile header and call-action links are icon-only with no aria-label, undetectable by screen readers | Fail | Medium | P2 | Automated | Kolli Balaji | 2026-08-30 | Cypress (accessibility.cy.js), Chrome/Electron, https://busybucketkb.vercel.app/ | See BUG_BB_004
TC_BB_038 | Accessibility | Color contrast ratios meet WCAG AA | 1. DevTools > Lighthouse > run Accessibility audit | N/A | No contrast failures flagged by Lighthouse; text meets 4.5:1 ratio | WCAG automated audit (cypress-axe) flagged contrast and layout validation errors on the page | Not Run | Medium | P2 | Manual | Kolli Balaji | 2026-08-30 | Cypress (accessibility.cy.js), Chrome/Electron, https://busybucketkb.vercel.app/ | See BUG_BB_003
TC_BB_039 | Accessibility | Focus indicators visible when tabbing | 1. Tab through the page 2. Observe visible outline/ring on focused element | Keyboard only | Focused element always visually identifiable, no missing outline |  | Not Run | Medium | P2 | Manual | Kolli Balaji
TC_BB_040 | Accessibility | Alt text on images/mascot SVGs | 1. Inspect each img/SVG element 2. Check alt attribute or title/aria-label | N/A | Meaningful images have descriptive alt text; decorative ones intentionally empty alt='' |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_041 | Edge Cases | Extremely slow network (3G throttle) | 1. DevTools > Network > throttle to 'Slow 3G' 2. Reload page | Slow 3G | Loading indicator shown, not a blank page during load | Simulated slow network via Cypress; app shows no loading screen/spinner during the delay window | Fail | Medium | P2 | Automated | Kolli Balaji | 2026-08-30 | Cypress (accessibility.cy.js), Chrome/Electron, https://busybucketkb.vercel.app/ | See BUG_BB_005
TC_BB_042 | Edge Cases | Offline mode handling | 1. DevTools > Network > check 'Offline' 2. Try to reload/interact | Offline | Clear offline message shown, not a broken blank page | Simulated offline state via Cypress; app shows no user-friendly offline message, likely renders broken/blank state | Fail | Medium | P2 | Automated | Kolli Balaji | 2026-08-30 | Cypress (accessibility.cy.js), Chrome/Electron, https://busybucketkb.vercel.app/ | See BUG_BB_006
TC_BB_043 | Edge Cases | Rapid repeated clicking on submit/CTA | 1. Click Book Now rapidly 5-10 times | N/A | Only one WhatsApp window/tab opens, no duplicate triggers | Cypress rapid-click test confirmed window.open is called multiple times with no debounce/throttle, causing duplicate WhatsApp triggers | Fail | High | P1 | Automated | Kolli Balaji | 2026-08-30 | Cypress (accessibility.cy.js), Chrome/Electron, https://busybucketkb.vercel.app/ | See BUG_BB_002
TC_BB_044 | Edge Cases | Browser back button after WhatsApp redirect | 1. Complete booking (redirect/new tab) 2. Click browser Back | N/A | Returns to sensible, non-broken state |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_045 | Edge Cases | JavaScript disabled fallback | 1. DevTools > Settings > Debugger > Disable JavaScript 2. Reload page | JS disabled | Some fallback message shown rather than fully blank page (document actual behavior) |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_046 | Edge Cases | Zooming in browser (150%, 200%) | 1. Ctrl/Cmd + Plus to zoom to 150%, then 200% | 150%, 200% zoom | Layout adapts without overlapping text or unusable buttons |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_047 | SEO/Meta | Page title and meta description present per route | 1. View Page Source (Ctrl+U) on each route 2. Check <title> and <meta name='description'> | All routes | Every page has unique descriptive title and meta description, not defaults |  | Not Run | Low | P3 | Manual | Kolli Balaji
TC_BB_048 | SEO/Meta | Open Graph tags for link previews | 1. View Page Source, search 'og:title', 'og:description', 'og:image' 2. Optionally test via Facebook Sharing Debugger/LinkedIn Post Inspector | Live site URL | All OG tags present and populated; link preview renders correctly when shared |  | Not Run | Medium | P2 | Manual | Kolli Balaji
TC_BB_049 | Security | No sensitive data exposed in client-side bundle | 1. DevTools > Sources > open main JS bundle 2. Search for 'key', 'secret', 'token', 'password', 'api_key' | N/A | No sensitive credentials/keys found in publicly downloadable bundle |  | Not Run | Critical | P1 | Manual | Kolli Balaji
TC_BB_050 | Security | Input sanitization on any free-text field | 1. Enter <script>alert(1)</script> into any text input 2. Observe how it's rendered back | XSS test string | Text rendered as plain visible text, not executed as code. N/A if no free-text fields exist |  | Not Run | High | P1 | Manual | Kolli Balaji

## Bug Report Log
Bug ID | Title | Module | Steps to Reproduce | Expected Behavior | Actual Behavior | Severity | Priority | Status | Environment/Browser | Reported By | Date Reported
BUG_BB_001 | Booking proceeds with silently defaulted service when no service is selected | Booking Flow | 1. Load site (city has default pre-selected)\n2a. Select a city, leave service untouched, click Book Now — OR —\n2b. Touch nothing at all, click Book Now immediately | Button should be disabled or show a validation prompt, since no service was actively selected by the user | App proceeds without validation in both paths. Fallback message text is inconsistent depending on interaction path — shows "cleaning services" when city was actively selected but service wasn't, vs generic "your services" when neither was touched. Indicates missing validation plus non-uniform fallback/default logic for the service field. | High | P1 | Open | Chrome 151, Windows 11, Desktop, 1440px | Kolli Balaji | 2026-08-29
BUG_BB_002 | Rapid CTA clicks trigger multiple WhatsApp windows (no debounce) | Booking Flow | Click Book Now rapidly 5-10 times in succession | Only one WhatsApp window/tab opens per booking action | window.open fires once per click with no throttling, opening multiple duplicate WhatsApp windows/tabs | High | P1 | Open | Cypress automated (booking-flow.cy.js) | Kolli Balaji | 2026-08-30
BUG_BB_003 | WCAG contrast/layout violations detected on main page | Accessibility | Run automated WCAG audit (cypress-axe) against the live page | No WCAG AA violations | Contrast and layout validation errors flagged by automated audit | Medium | P2 | Open | Cypress + cypress-axe (accessibility.cy.js) | Kolli Balaji | 2026-08-30
BUG_BB_004 | Icon-only mobile header/call links missing aria-labels | Accessibility | Inspect mobile header and call-action icon links for accessible name | All icon-only interactive elements have aria-label or equivalent accessible text | Mobile header and call links have no aria-label, unreadable by screen readers | Medium | P2 | Open | Cypress + cypress-axe (accessibility.cy.js) | Kolli Balaji | 2026-08-30
BUG_BB_005 | No loading indicator shown during slow network conditions | Edge Cases | Throttle network to Slow 3G (or simulate via Cypress intercept delay), reload page | Loading spinner/indicator shown during load delay | No loading UI present; page appears blank/frozen during delay | Medium | P2 | Open | Cypress (edge-cases.cy.js) | Kolli Balaji | 2026-08-30
BUG_BB_006 | No offline message shown when connection drops | Edge Cases | Simulate offline state (DevTools/Cypress network mock), attempt to interact | Clear "you're offline" message shown to user | No offline messaging; app shows broken/blank state | Medium | P2 | Open | Cypress (edge-cases.cy.js) | Kolli Balaji | 2026-08-30
BUG_BB_007 | Swipe-back navigation gesture after selection leads to blank 404 page | Routing / Navigation | 1. On mobile, select one or more services\n2. Perform a right-to-left edge swipe (native browser back gesture)\n3. Observe result | Should return to previous valid app state or homepage | Page goes blank and displays a 404 Not Found error | High | P1 | Open | Chrome 151, Windows 11, Desktop, 1440px | Kolli Balaji | 2026-08-30

## Test Summary Report
Test Summary Report — Busy Bucket
Project Name
Test Cycle / Date Range
Tested By
Total Test Cases | 50
Passed | 19
Failed | 10
Blocked | 0
Not Run | 19
Pass Rate (%) | 38%
Total Bugs Logged | 7
Critical/High Bugs Open | 3
Overall Status